## Action Plan
ACTION PLAN
PROJECT NAME | PROJECT MANAGER
Improve the analytical lab efficiency | Ben Xu
ACTION | RESPONSIBLE | PRIORITY | STATUS | START | END | NOTES
Goal #1: Provide crosstraining
Identify the gaps for skillsets | Ben Xu | High | In progress | 2022-09-30 | 2022-10-02
develop SOPs | Mike Hess | High | In progress | 2022-10-05 | 2022-10-09 | Must send contracts by 10/10
Provide trainings | Mike Hess | High | Not started | 2023-01-30 | 2023-06-24
evalute the results of the training | Ben Xu | High | Not started | 2/30/2023 | 2023-06-24
Goal #2: Improve analytical lab report quality
Analyze the current lab report | Ben Xu | High | In progress | 2022-10-07 | 2022-10-12
Identify the gaps for lab report quality | Ben Xu | Medium | Not started | 2023-10-12 | 2023-10-14
Develop method to close the gap | Ben Xu | Medium | Not started | 2023-10-13 | 2023-10-16 | Send to stakeholders
Implement the changes | Ben Xu | High | Not started | 2023-10-17 | 2023-10-18
Goal #3: External lab testing
Identify the tests need to be sent out | Ben Xu | High | In progress | 2022-10-13 | 2023-10-19
Write up vendor agreement | Ben Xu | Medium | Not started | 2023-10-15 | 2023-10-16
Decide the price and turn around time | Ben Xu | High | In progress | 2022-10-19 | 2023-10-21
Annouce the options to stake holders | Ben Xu | Medium | Not started | 2023-10-21 | 2023-10-23 | From sales team